## Closeout Status
Subcontractor | Spec | Description | Warranty | O&M | As-Built Drawings | Attic Stock | Training | Notes
ABC Electric | Div 1 | General Warranty | Required
ABC Electric | 26 0526 | Grounding and Bonding |  | Required
ABC Electric | 26 0943 | Lighting Controls | Required | Required | Required |  | Required | Need factory training scheduled
ABC Electric | 26 5100 | Interior Lighting | Required | Required |  | 2 per type
ABC Electric | 27 1500 | Data System | Required | Required
Acme Plumbing Inc. | Div 1 | General Warranty | Complete |  | Complete
Acme Plumbing Inc. | 22 0500 | Common Work Results | Complete | X
Acme Plumbing Inc. | 22 1116 | Domestic Water Piping |  | Complete
Acme Plumbing Inc. | 22 4000 | Plumbing Fixtures | Required | Complete |  |  | Required
SteelCo Construction, LLC | 05 1200 | Structural Steel | X, SHOP DWGS | X, SHOP DWGS
SteelCo Construction, LLC | 05 2100 | Steel Joist Framing |  | X, SHOP DWGS
SteelCo Construction, LLC | 05 5000 | Metal Fabrications |  | Complete
JB Concrete | Div 1 | General Warranty | Complete
JB Concrete | 03 3000 | Cast-in-Place Concrete | Complete
JB Concrete | 07 1113 | Dampproofing | X
Midwest Painting Co. | Div 1 | General Warranty | Complete | Complete
Midwest Painting Co. | 09 9123 | Interior Painting |  |  |  | 5% but not less than 1 gal per color |  | Need color schedule
Summit Roofing | Div 1 | General Warranty | Required
Summit Roofing | 07 3113 | Asphalt Shingles | Required | Required |  | 100 SQ FT
Summit Roofing | 07 5419 | PVC Roofing | Required | Required |  |  |  | Waiting on manufacturer warranty cert
HVAC Systems Co. | 23 0000 | HVAC | Complete | Required |  |  |  | Some received, Mark needs to review
HVAC Systems Co. | 23 0800 | Commissioning |  | Required | Required |  | Required
HVAC Systems Co. | 23 3300 | Air Duct Accessories |  | Required |  | 10% of fusible links |  | Still waiting on damper submittals
HVAC Systems Co. | 23 7313 | Air Handling Units |  | Required |  |  | Required | Factory training rescheduled to April
Valley Landscaping | Div 1 | General Warranty | Required |  |  |  |  | Promised by next week
Valley Landscaping |  | Landscaping | Required | Required | Required | NA
SteelCo Construction | 05 3100 | Steel Decking |  | X, MILL CERTS